## Gantt Chart
Task | Start Date | Duration (days)
Define business problem & solution | 2026-03-01 | 3
Design UI/UX wireframes (Figma) | 2026-03-04 | 5
Create GitHub repo + README | 2026-03-09 | 2
Create Gantt chart | 2026-03-11 | 1
Design database schema | 2026-03-16 | 3
Build backend API (CRUD) | 2026-03-19 | 7
Build frontend UI components | 2026-03-26 | 7
Connect frontend to backend | 2026-04-02 | 5
Add low-stock alert feature | 2026-04-07 | 4
Testing and bug fixes | 2026-04-11 | 4
Final report + presentation slides | 2026-04-15 | 5